## Sheet1
QA Test Plan – Digital Library Management System
Project Name: Digital Library Management System
Module: Full System Testing
QA Lead: Khethiwe Skosana
Date: 04 September 2025
Test ID | Feature / Module | Test Scenario | Steps | Expected Result | Actual Result | Status | Remarks
TC001 | Login | Valid credentials | Enter correct username & password | Redirect to dashboard | Redirected to dashboard | Pass | Works
TC002 | Login | Invalid password | Enter wrong password | “Invalid credentials” error | “Invalid credentials” error | Pass
TC003 | Search Books | Search by title | Search “Database Systems” | Matching list displayed | Matching list displayed | Pass
TC004 | Borrow Book | Available book | Borrow “Java Programming” | Confirmation + due date | Confirmation shown | Pass
TC005 | Borrow Book | No copies available | Borrow “Python Basics” (0 copies) | “Book unavailable” error | “Book unavailable” error | Pass
TC006 | Return Book | Return borrowed book | Return “Java Programming” | Status updated to returned | Status updated | Pass
TC007 | Manage Books | Admin adds book | Add “Networking Essentials” | Book in catalog | Book appears in catalog | Pass
TC008 | Manage Books | Admin edits book | Change title to “Networking Essentials 2nd Ed” | Updated details | Updated details | Pass
TC009 | Manage Books | Admin deletes book | Delete “Old Book” | Book removed | Book removed | Pass
TC010 | Security | SQL Injection | Try ' OR 1=1 -- login | Login fails | Login fails | Pass | Prevented injection
TC011 | Performance | Search under load | 200 concurrent searches | < 2s response | Avg 1.8s | Pass
TC012 | Accessibility | Screen reader | Open site with reader | All elements read | Menu skipped | Fail | Needs ARIA labels